## Sheet1
Break Down - Fusion (Days) |  |  |  | What I'm Working on now
| Worst Case Estimate | Actual | Best Case Estimate
Work Items
Work Items Edit Has Either Image Control Or Media Control | 2 | 0 | 1
Work Items Search (Pillars & Categories) | 2 | 0 | 1
Media Items Search (Pillars & Categories) | 2 | 0 | 1
Edit Items Edit Has Either Image Control Or Media Control | 2 | 0 | 1
Filter to single user & all for admin user
Release A work item, close status
Categories & Pillars Are Mutually Exclusive
Image Cropper | 3 | 3 | 2
Image Cropper to Send Image Up Through Web API
Creates a clip in a file group for that media item
Clipfile Server Base
Media Editor | 5 | 3 | 2
Media Editor To Take Start & End Date of video streamed
Processing done inside application pool on the web api
Clipfile Server Base
Role Management (Done to a degree) | 5 | - | 2
Request New Attribute Email Fire | 1 | - | 0.5
Just an email to all stewards to add an attribute
Lookups | 1 |  | 0.5
Recommend Recent Value |  | 0
Recommend Most Used |  | 0
Lookup Email Fire |  |  | 0.5
Just an email to all stewards to add a lookup |  | 1
Attribute Default | 7 |  | 2
Default Page Search To Select Default Attributes |  | 3
Insert Default Page on Client
Insert Default Page on Channel
Insert Default Page On Attributes
On Default Edit Page There Is A list (No Paging) |  | 3
Pivot on Page - One For Search One For Add
Add Pivot Has Drop Down Of Attribute Type
Add Pivot Page Has Drop Down of Start Date, End Date, Time.
Add Pivot Page Intantiates Control According to Drop Down (According to attribute)
Creation Of Media Item Creation In Service - media item properties applied | 3 |  | 1
Total | 33 | 13 | 14.5